## Slide 1: Remote Support
Patty Lindsay

## Slide 2: Substantial Material Available
Remote Support Workflow
  This describes the high level process of how tasks flow as RS is notified, activated, made operational, and demobilized.
Personnel Requirements
  Skills and equipment required to participate in RS
Training Curriculum
  Lists skills to be taught, and references materials to be used for training

## Slide 3: Substantial Material Available
Documents available here:
____________
Training Materials and Operational Documents
  Documents used for training and/or reference or during operations.
Supporting documents
  Forms and Reference materials that can be used to implement procedures.

## Slide 4: Current Status
Practical assessments needed:
  Conference-level review for suitability.
  Beta testing via simulated exercise.
  Limited roll-out
Assessments will:
  inform changes to materials
  better directing future efforts.

## Slide 5: Conference-level Review
To identify compatibility with current ASRC procedures and documentation
To integrate tools available to the conference
To integrate knowledge available in the conference

## Slide 6: Beta Testing via Simulated Exercise
Will require participants and observers
  Participants will receive a brief training, then use the procedures and other materials to provide RS to a mock search.
  Observers will be tasked with identifying gaps and areas where further information/documentation is needed.
  Both will report back to RS Group with suggested improvements

## Slide 7: Limited Rollout
Will involve one or two teams that already are providing some level of remote support on an ad-hoc basis.
Teams will be asked to provide feedback to RS group.

## Slide 8: Future Work
Feedback will drive future efforts
  Revision of existing documents
    Many documents are drafts, need testing. Feedback will help identify errors, inconsistencies, and clarity improvements
  Develop new Documentation
    As training material, procedures, curricula, or workflows are altered, additional documentation may be needed. This may include new training materials, new forms, and other such documents as needed.

## Slide 9: Action Items
Who to review, by when?
Recruit lead to develop mock and recruit participants
Small scale trial - recruit two teams